## Sheet1
SEVERITY
| Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level |  |  | Minimal | Minor | Moderate | Major | Severe
1 | Strain injuries | Working for too long may induce strain injury | Get up and move around every now and again | Maintain a reasonable level of comfort while working | Expected | Minimal | 4 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | Fail to achieve a work-life balance between project and normal work | Juggling between project and normal duties may prove to be very difficult | Keep communicating with training providers and line manager to manage expectations and timeslots | Maintaing a good work schedule and escalating concerns | Likely | Severe | 15 |  | Expected | 4 | 8 | 12 | 16 | 20
3 | Steep configuration curve | Unfamiliar technologies can take a long time to setup | Search in trouble-shooting guides such as StackOverflow how to get past any configuration errors | Find good tutorials explaining setup processes | Likely | Severe | 15 |  | Likely | 3 | 6 | 9 | 12 | 15
4 | Lack of application documentation | Documenting how to run the application and its design might be left for the last moment | Document every bit in the project management part of the section after small incremental developments. Use tasks and user stories for this. | Write documentation after completing each task and user story | Unlikely | Major | 4 |  | Possible | 2 | 4 | 6 | 8 | 10
5 | Lack of project management documentation | A deep dive into technical aspects and development might overshadow managing tasks, user stories and documentation | Start with project management aspect by outling Epics of tasks/user stories to define a project structure before commencing any deep technical work | Maintain an agile way of defining user story, developing the feature and then documenting the user story | Unlikely | Major | 4 |  | Unlikely | 1 | 2 | 3 | 4 | 5
6 | Lose access to development tools such as laptop | Losing access to Internet or personal machine can block me from doing tasks related to the project | Escalate concerns to training providers and line manager and seek backup machine to setup from remote resources. | Keep all relevant project files on cloud providers (Jira for project management, Github for project code and Google office for documents). | Possible | Severe | 10
7 | Lack of feature testing | Lack of unit testing may result in an application that has bugs in the functional logic | Ensure that every code related to a user story has been tested before moving to the next one. | Maintain an agile iteration of defining user story, developing the feature and then unit testing the bit of code that represents that feature. | Unlikely | Major | 4
8 | Application's virtual machine goes down | Application goes offline | Recreate infrastucture on another machine | Use infrastructure as code to quickly recreate machine & store all code in VCS | Unlikely | Major | 5
9 | Broken version deployed onto production | Deployed product may have issues or missing requirements | Revert production to most recent stable version | Automate tests before any deployment & restrict access to production branch | Unlikely | Major | 10
10 | Possibility of someone in the team accidentally sharing secret credentials for the application | A team member leaves credentials in an unsafe location and they get seen by a potentially malicious user | Reset passwords of all accounts and/or disable access to all affected ones via permission roles. | Keep roles of priviliges on a need-to-know basis and ensure that every member of the team does not download credentials files offline from the secure server. Enable 2-Factor-Authentication on all accounts. | Unlikely | Major | 10